## Dashboard
Task ID | Task Name | Team | Task Owner | Start Date | Due Date | Task Duration | Status | Overdue? | Comments
T001 | Prepare Q4 Financial Report | Finance | Sarah Johnson | 2025-09-02 | 2025-09-20 | 18 | Completed | FALSE | Submitted to CFO for review.
T002 | Conduct Market Research | Strategy | Sarah Johnson | 2025-09-05 | 2025-09-25 | 20 | Completed | FALSE | Draft findings ready; awaiting survey data.
T003 | Redesign Website Homepage | Strategy | David Kim | 2025-07-10 | 2025-08-05 | 26 | Completed | FALSE | Wireframes approved; development in progress.
T004 | Update Sales Forecast for FY2026 | Finance | Sarah Johnson | 2025-09-12 | 2025-09-30 | 18 | Not Started | TRUE | Final version shared with Sales Director.
T005 | Implement CRM Upgrade | Strategy | James Miller | 2025-09-15 | 2025-10-10 | 25 | Completed | FALSE | Vendor confirmed delivery timeline.
T006 | Plan Annual Company Retreat | HR | David Kim | 2025-09-18 | 2025-10-15 | 27 | In Progress | TRUE | Venue options being shortlisted.
T007 | Review Legal for Contracts | HR | Alex Chen | 2025-08-20 | 2025-08-27 | 7 | Completed | FALSE | Updated contracts aligned with new regulation.
T008 | Launch Social Media Campaign | Marketing | Alex Chen | 2025-09-22 | 2025-10-12 | 20 | In Progress | TRUE | Initial creatives approved, campaign scheduled.
T009 | Recruit New Data Analyst | HR | Sarah Johnson | 2025-09-23 | 2025-10-20 | 27 | Completed | FALSE | First round of interviews completed.
T010 | Conduct Employee Survey | HR | Sarah Johnson | 2025-09-24 | 2025-10-05 | 11 | In Progress | TRUE | Survey questions finalized.
T011 | Prepare Investor Presentation | Finance | David Kim | 2025-09-25 | 2025-10-02 | 7 | Completed | FALSE | Draft slides ready; awaiting financial highlights.
T012 | Upgrade Infrastructure | Strategy | Sarah Johnson | 2025-09-26 | 2025-10-30 | 34 | Completed | FALSE | External consultant engagement pending.
T013 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2025-09-27 | 2025-10-07 | 10 | In Progress | TRUE | Three proposals shortlisted for management review.
T014 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2025-09-28 | 2025-10-18 | 20 | Completed | FALSE | Kick-off meeting scheduled next week.
T015 | Audit Internal Expense Reports | Finance | Emily Davis | 2025-09-29 | 2025-10-04 | 5 | In Progress | TRUE | Waiting for submission of all departmental reports.
T016 | Analysis of big data | Finance | Alex Chen | 2025-11-30 | 2025-12-13 | 13 | Not Started | TRUE | Waiting for the permission to access the clients data
T017 | Recruit New Data Analyst | HR | Alex Chen | 2025-12-14 | 2025-12-20 | 6 | Completed | FALSE | Submitted the reports and the names of selected data analysts
T018 | Recruit Interns | HR | David Kim | 2025-12-16 | 2025-12-30 | 14 | In Progress | TRUE | The interviews are still on going
T019 | Annual financial report | Finance | David Kim | 2025-12-17 | 2025-12-27 | 10 | Completed | FALSE | Submitted the financial report
Formulas:
Overdue? = AND(Table1[[#This Row],[Status]]<>"Completed",Table1[[#This Row],[Due Date]]<TODAY())
TASK MANAGEMENT TRACKER
Complete
11
Not Started
2
In Progress
6
Total
19
OVERDUE
8
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Support Sheet
Status | Count | Owners | Count | Team | Count | Overdue
Completed | 11 | Sarah Johnson | 6 | Finance | 6 | 8
In Progress | 6 | David Kim | 5 | Strategy | 6
Not Started | 2 | James Miller | 1 | HR | 6
Total | 19 | Alex Chen | 4 | Marketing | 1
|  | Emily Davis | 3

## Sheet1
Row Labels | Count of Task Duration | Row Labels | Count of Task Duration
Finance | 6 | Alex Chen | 4
HR | 6 | David Kim | 5
Marketing | 1 | Emily Davis | 3
Strategy | 6 | James Miller | 1
Grand Total | 19 | Sarah Johnson | 6
|  | Grand Total | 19
Row Labels | Sum of Count
Completed | 11
In Progress | 6
Not Started | 2
Total | 19

## Sheet2
Row Labels | Count of Task ID
Alex Chen | 4
David Kim | 5
Emily Davis | 3
James Miller | 1
Sarah Johnson | 6
Grand Total | 19

## Sheet3
Data returned for Count of Task Duration, Emily Davis (First 1000 rows).
Range[Task ID] | Range[Task Name] | Range[Team] | Range[Task Owner] | Range[Start Date] | Range[Due Date] | Range[Task Duration] | Range[Status] | Range[Overdue?] | Range[Comments]
T013 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2025-09-27 | 2025-10-07 | 10 | In Progress | TRUE | Three proposals shortlisted for management review.
T014 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2025-09-28 | 2025-10-18 | 20 | Completed | FALSE | Kick-off meeting scheduled next week.
T015 | Audit Internal Expense Reports | Finance | Emily Davis | 2025-09-29 | 2025-10-04 | 5 | In Progress | TRUE | Waiting for submission of all departmental reports.